## Risks
RAID Log — Risks
BBA Institute Template ¦ bba.institute
ID | Date Raised | Category | Description | Probability (H/M/L) | Impact (H/M/L) | Risk Score | Owner | Mitigation Strategy | Contingency Plan | Status | Review Date
R001 | 2024-01-15 | Technical | Integration with legacy CRM may fail due to deprecated API | H | H |  | Jane Smith | Engage vendor for API upgrade path; build adapter layer | Implement manual data sync as fallback | Open | 2024-02-15
R002 | 2024-01-16 | Resource | Key SME unavailable during UAT phase | M | H |  | Tom Lee | Book SME availability 4 weeks ahead; document knowledge | Extend UAT timeline by 2 weeks | Open | 2024-02-01
R003 | 2024-01-20 | Scope | Stakeholder scope creep on reporting module | H | M |  | Sarah Park | Formal change control process; weekly scope reviews | Descope non-essential reports to Phase 2 | Monitoring | 2024-02-20

## Assumptions
RAID Log — Assumptions
BBA Institute Template ¦ bba.institute
ID | Date Raised | Assumption | Rationale | Owner | Impact if Wrong | Validation Method | Validated? | Notes
A001 | 2024-01-15 | Users have access to modern browsers (Chrome/Firefox/Edge) | IT policy mandates supported browser list | IT Lead | UI functionality may be limited | IT policy review | Yes
A002 | 2024-01-16 | Current data quality is sufficient for migration | Data profiling not yet complete | Data Analyst | Data cleansing effort may triple | Data profiling report | Pending | Review due Feb 1
A003 | 2024-01-18 | Business will complete UAT within 2 weeks | Based on prior project history | PM | Project go-live delayed | Resource commitment sign-off | No | Awaiting sponsor confirmation

## Issues
RAID Log — Issues
BBA Institute Template ¦ bba.institute
ID | Date Raised | Priority (H/M/L) | Description | Impact | Owner | Action Required | Target Date | Resolution | Status | Date Closed
I001 | 2024-01-22 | H | UAT environment not available — blocking testing | Testing cannot commence; 5 days delay already | Dev Lead | Provision UAT environment in AWS | 2024-01-25 |  | Open
I002 | 2024-01-23 | M | Conflicting requirements from two business units | Requirements document incomplete | BA Team | Facilitated requirements workshop with both BUs | 2024-01-30 | Workshop held; agreed version signed off | Closed | 2024-01-31

## Dependencies
RAID Log — Dependencies
BBA Institute Template ¦ bba.institute
ID | Dependency Description | Type (Internal/External) | Project/Team | Dependent On | Required By Date | Owner | Status | Risk if Delayed | Notes
D001 | Data migration from legacy ERP must complete before UAT | Internal | ERP Replacement | Data Warehouse Team | 2024-02-15 | Data Architect | On Track | UAT delayed if data not ready
D002 | Third-party payment gateway API credentials | External | Finance / Vendor | Payment Gateway Vendor | 2024-02-01 | Tech Lead | At Risk | Payment module cannot be tested | Vendor SLA response pending