## RACI Matrix
RACI Matrix
R=Responsible A=Accountable C=Consulted I=Informed ¦ bba.institute
# | Activity / Deliverable | Phase | Project Sponsor | Business Owner | Project Manager | Business Analyst | Tech Lead | Developer | QA Lead | UX Designer | Change Manager | End Users
1 | Project Charter sign-off | Initiation | A | R | C | I | I | I | I | I | I | I
2 | Business Case development | Initiation | A | C | R | C | I | I | I | I | I | I
3 | Stakeholder identification & analysis | Planning | I | C | C | R | I | I | I | C | I | I
4 | Requirements elicitation workshops | Planning | I | A | C | R | C | I | I | C | I | C
5 | Business Requirements Document (BRD) | Planning | A | C | C | R | C | I | I | I | I | I
6 | Functional Specification | Planning | I | A | C | R | C | C | I | C | I | I
7 | Solution design review | Design | I | A | I | C | R | C | C | C | I | I
8 | UX/UI wireframes approval | Design | I | A | I | C | C | I | I | R | I | C
9 | Development sprints | Build | I | I | C | C | A | R | C | I | I | I
10 | System Integration Testing (SIT) | Test | I | I | C | C | A | R | R | I | I | I
11 | User Acceptance Testing (UAT) | Test | I | A | C | R | C | I | C | I | I | R
12 | Defect triage & resolution | Test | I | I | C | C | A | R | R | I | I | I
13 | Training material development | Deployment | I | C | C | R | I | I | I | I | C | I
14 | Go-live approval | Deployment | A | R | C | I | I | I | I | I | C | I
15 | Post-implementation review | Closure | A | R | R | C | C | I | C | I | I | I
LEGEND
R = Responsible — does the work |  | A = Accountable — owns outcome | R: C = Consulted — input required; I: I = Informed — kept in the loop