## Stakeholder Register
Stakeholder Register & Analysis
bba.institute
ID | Name | Organisation / Dept | Role / Title | Influence (H/M/L) | Interest (H/M/L) | Impact (H/M/L) | Current Attitude | Desired Attitude | Engagement Strategy | Communication Channel | Frequency | Key Concerns / Needs | Notes
S001 | Emma Clarke | Executive | CFO | H | H | H | Supportive | Champion | Regular executive briefings; early wins shown; ROI emphasis | Executive Briefing | Fortnightly | Cost overruns; compliance risk; timeline | Sponsor champion — keep close
S002 | David Nguyen | IT | CTO | H | M | H | Neutral | Supportive | Involve in architecture decisions; technical demos | Steering Committee | Monthly | Legacy system impact; security; data integrity | Key decision-maker on tech approach
S003 | Priya Patel | Operations | Ops Manager | M | H | H | Resistant | Neutral | 1:1 sessions; show how pain points solved; include in pilots | Email + Workshop | Weekly | Disruption to daily operations; staff workload | Change champion potential if won over
S004 | James Wright | Finance | Finance Analyst | L | M | M | Neutral | Supportive | Newsletter updates; include in UAT | Email | Monthly | Reporting accuracy; interface usability | Will be heavy user of reporting module
S005 | Sandra Brown | HR | HR Director | M | L | M | Unaware | Informed | Awareness sessions; training plan overview | Town Hall + Email | Quarterly | Staff morale; training availability | Needs comms on change impact for teams
S006 | Michael Torres | External | Regulator | H | L | H | Neutral | Supportive | Formal compliance reporting; early notification of changes | Formal Report | Quarterly | Regulatory compliance; audit trail | Legal obligation to keep informed

## Power-Interest Grid
Stakeholder Power-Interest Grid
Plot stakeholders by influence vs. interest
| ← LOW INTEREST | HIGH INTEREST →
HIGH POWER ↑ | KEEP SATISFIED (High Power, Low Interest) Manage carefully — keep happy without overloading with info | MANAGE CLOSELY (High Power, High Interest) Key stakeholders — maximum engagement and communication
LOW POWER ↓ | MONITOR (Low Power, Low Interest) Minimal effort — general updates only | KEEP INFORMED (Low Power, High Interest) Regular updates — no major decisions required