## RTM
Requirements Traceability Matrix (RTM)
bba.institute
Req ID | Business Objective | Requirement Description | Priority (MoSCoW) | Source | Functional Spec Ref | Design Ref | Test Case ID(s) | UAT Test Ref | Status | Owner | Notes
REQ-001 | Increase user efficiency | System shall allow single sign-on via corporate IdP | Must Have | BRD §2.1 | FS-001 | DES-001 | TC-001, TC-002 | UAT-001 | In Progress | BA Team | Linked to security policy
REQ-002 | Data integrity | System shall validate all mandatory fields before submission | Must Have | Workshop 3 | FS-002 | DES-005 | TC-010-014 | UAT-002 | Complete | Dev Team
REQ-003 | Reporting | System shall generate weekly performance reports in Excel/PDF | Must Have | CFO Interview | FS-010 | DES-012 | TC-050 | UAT-010 | Not Started | Report Dev | Format TBC
REQ-004 | User experience | Users shall complete key tasks in ≤ 3 clicks | Should Have | UX Research | FS-015 | DES-020 | TC-060 | UAT-020 | In Progress | UX Team | Usability test planned
REQ-005 | Compliance | System shall maintain full audit log for 7 years | Must Have | Legal | FS-020 | DES-025 | TC-070-072 | UAT-025 | Not Started | Tech Lead | ISO 27001 requirement
REQ-006 | Performance | Page load time shall be < 2 seconds at 500 concurrent users | Should Have | IT Strategy | FS-025 | DES-030 | TC-080 | UAT-030 | Not Started | Perf Team | Load test required
REQ-007 | Accessibility | Interface shall meet WCAG 2.1 AA standard | Should Have | HR Policy | FS-028 | DES-035 | TC-085 | UAT-035 | Not Started | UX Team
REQ-008 | Notifications | System shall send email/SMS alerts for key events | Could Have | User interviews | FS-030 | DES-040 | TC-090 | UAT-040 | Not Started | Dev Team | Phase 2 candidate
REQ-009 | Mobile | Core functions available on iOS and Android | Could Have | Mobile survey | FS-035 | DES-045 | TC-095 | UAT-045 | Not Started | Mobile Team | Native vs PWA TBC
REQ-010 | Integration | Sync with Salesforce CRM daily | Must Have | Sales Director | FS-040 | DES-050 | TC-100 | UAT-050 | At Risk | Integration Team | API contract pending