## Gap Analysis
Gap Analysis
bba.institute ¦ Current State → Future State → Gap → Action
# | Business Capability / Process | Current State (AS-IS) | Desired State (TO-BE) | Gap Description | Gap Type | Gap Size (H/M/L) | Priority (H/M/L) | Recommended Action | Owner | Timeline | Status
1 | Customer Onboarding | Manual paper forms, 3-day processing time, error rate ~15% | Digital online form, 24hr processing, automated validation, <1% error | No digital capture; no automated validation; no audit trail | Process & Technology | H | H | Implement online form with field validation + automated workflow | Ops Manager + IT Lead | Q2 2024 | Open
2 | Reporting | Monthly manual Excel reports; 2-day prep time; no real-time view | Self-service dashboards; real-time data; automated daily refresh | No BI tool; data siloed across 3 systems; no single source of truth | Technology & Data | H | H | Deploy Power BI + data warehouse; consolidate source systems | Analytics Team | Q3 2024 | In Progress
3 | Staff Onboarding | 30-page PDF handbook; verbal briefings; no tracking | LMS-based module; digital sign-off; completion tracking | No structured digital training path; no tracking; inconsistent delivery | Process | M | M | Build LMS onboarding course with digital assessment and sign-off | HR Lead | Q3 2024 | Planned
4 | Contract Management | Email and shared drive; version confusion; no expiry alerts | Central contract repository; version control; automated renewal alerts | No contract lifecycle management; risk of missed renewals | Technology | M | H | Procure contract management SaaS (e.g. Ironclad, ContractPodAi) | Legal + Procurement | Q4 2024 | Open
5 | Customer Feedback | Post-call email surveys; 8% response rate; no analysis | In-app surveys; real-time NPS; sentiment analysis; action workflow | No in-app mechanism; low response; no action loop for poor feedback | Process & Technology | M | M | Integrate Medallia or Qualtrics; build CX feedback workflow | CX Team | Q4 2024 | Open