## Comms Plan
Stakeholder Communication Plan
bba.institute
ID | Stakeholder / Group | Communication Objective | Content / Key Messages | Channel | Format | Frequency | Owner | Next Due Date | Notes
C-001 | Project Sponsor | Keep informed of progress; flag issues early | Project status, budget, risk, decisions required | 1:1 meeting + status report | Slide deck (3 slides max) | Fortnightly | PM | [Date] | Escalate any red items 48hr before
C-002 | Steering Committee | Governance oversight; approve major decisions | Milestone status, budget variance, risks, change requests | Steering meeting | Formal presentation | Monthly | PM | [Date] | Papers circulated 5 days prior
C-003 | Business Owner | Requirements sign-off; UAT engagement | Requirements updates, UAT plan, decisions needed | Teams call + email | Status update email | Weekly | BA Lead | [Date] | CC department heads on major updates
C-004 | Business Analysts (team) | Alignment on tasks, blockers, priorities | Sprint plan, open actions, blockers, requirements updates | Stand-up + Jira | Verbal + Jira board | Daily | BA Lead | [Date] | 15-min daily stand-up
C-005 | Development Team | Technical clarity; dependency management | Approved requirements, sprint backlog, defects | Jira + Dev meeting | Jira tickets + meeting | Weekly | Tech Lead | [Date] | BA attends sprint planning
C-006 | End Users / Business Staff | Awareness of change; reduce resistance | What's changing, when, how it affects them, training plan | All-hands session + email | Newsletter + presentation | Monthly + key milestones | Change Manager | [Date] | Tone: reassuring, benefit-focused
C-007 | IT Operations | Infra readiness; deployment planning | Environment requirements, deployment schedule, support handover | Technical meeting | Technical doc + meeting notes | Fortnightly | Tech Lead | [Date]
C-008 | Legal / Compliance | Regulatory compliance sign-off | Data handling approach, privacy impact, contract requirements | Email + formal review | Compliance review doc | At key milestones | PM | [Date] | Minimum 2 weeks lead time
C-009 | External Vendor | Delivery status; issue resolution | Integration milestones, defects, change requests | Email + video call | Email + meeting notes | Weekly during integration | Tech Lead | [Date] | Use formal change request for scope changes
C-010 | All Project Team | Team cohesion; broader awareness | Sprint demos, project wins, upcoming milestones | Team newsletter + Slack | Short update email | Fortnightly | PM | [Date] | Keep to <5 min read