## Product Backlog
Product Backlog Template
bba.institute
Story ID | Epic | User Story | Acceptance Criteria | Story Points | Priority (MoSCoW) | Sprint | Status | Business Value | Owner | Notes
US-001 | Authentication | As a new user, I want to register with email and password so that I can access the platform | • Registration form validates email format • Password must be 8+ chars with 1 number • Verification email sent within 2 min • Duplicate email shows error | 5 | Must Have | Sprint 1 | Done | High | Dev Team
US-002 | Authentication | As a registered user, I want to log in with my credentials so that I can access my account | • Login with correct credentials succeeds • Wrong credentials shows error • Account locks after 5 failed attempts | 3 | Must Have | Sprint 1 | Done | High | Dev Team
US-003 | Authentication | As a user, I want to reset my password via email so that I can recover access to my account | • Reset email received within 5 min • Link expires in 24 hours • New password accepted; old rejected | 3 | Must Have | Sprint 2 | In Progress | High | Dev Team
US-004 | Profile | As a user, I want to update my profile information so that my account details stay current | • Fields: name, phone, address • Changes saved and confirmed • Audit log entry created | 2 | Must Have | Sprint 2 | To Do | Medium | Dev Team
US-005 | Product Catalogue | As a shopper, I want to browse products by category so that I can find relevant items quickly | • Category filter updates results in real-time • Empty state shown if no results • Loading state shown while fetching | 5 | Must Have | Sprint 2 | To Do | High | Dev Team
US-006 | Product Catalogue | As a shopper, I want to search for products by keyword so that I can find specific items fast | • Search results in ≤1 second • Partial match supported • No results state handled | 8 | Must Have | Sprint 3 | To Do | High | Dev Team | Elastic Search integration
US-007 | Cart | As a shopper, I want to add items to a cart so that I can purchase multiple products at once | • Add button on product card and detail • Cart persists across sessions • Quantity adjustable; remove available | 5 | Must Have | Sprint 3 | To Do | High | Dev Team
US-008 | Checkout | As a shopper, I want to checkout and pay so that I can complete my purchase | • Address, payment, order review steps • Stripe + PayPal supported • Confirmation page + email on success | 13 | Must Have | Sprint 4 | To Do | High | Dev Team
US-009 | Orders | As a customer, I want to view my order history so that I can track and reference past purchases | • Orders listed newest first • Click-through to order detail • Status shown accurately | 5 | Should Have | Sprint 4 | To Do | Medium | Dev Team
US-010 | Notifications | As a customer, I want to receive an order confirmation email so that I have a record of my purchase | • Email within 5 min of purchase • Contains order ref, items, total, delivery info | 3 | Must Have | Sprint 4 | To Do | High | Dev Team | SendGrid
US-011 | Wishlist | As a shopper, I want to save items to a wishlist so that I can purchase them later | • Add from product page • Wishlist persists in account • Move to cart from wishlist | 3 | Should Have | Sprint 5 | To Do | Medium | Dev Team
US-012 | Reviews | As a customer, I want to leave a product review so that I can share my experience | • Rating 1-5 stars + text comment • Verified purchase badge on review • Review moderation queue for admin | 5 | Could Have | Backlog | To Do | Medium | Dev Team | Phase 2 candidate