## UAT Plan
UAT Test Plan
bba.institute
Project | [Project Name]
UAT Phase | UAT Phase [N]
Start Date | [DD-MM-YYYY]
End Date | [DD-MM-YYYY]
UAT Lead | [Name]
Business Owner | [Name]
SCOPE
What IS covered: [list features/modules in scope] What is NOT covered: [list out-of-scope items]
ENTRY CRITERIA
• All SIT defects Severity 1 & 2 resolved • UAT environment deployed and stable • Test data prepared and seeded • UAT participants confirmed and available
EXIT CRITERIA
• All test scripts executed • 100% of critical/high defects resolved • Business Owner sign-off obtained • UAT sign-off document completed
ENVIRONMENT
URL: [UAT URL] Login: [test credentials] Data: [description of test data set]
UAT SCHEDULE
Phase | Activity | Owner | Date | Duration
Preparation | Prepare test data, brief testers | UAT Lead | [Date] | 2 days
Execution Week 1 | Execute test scripts — core flows | Business users | [Date] | 5 days
Execution Week 2 | Execute test scripts — edge cases + regression | Business users | [Date] | 5 days
Defect Resolution | Developer fixes; BA verification | Dev + BA | [Date] | 3 days
Sign-off | Final review, sign-off meeting | Business Owner | [Date] | 1 day

## Test Scripts
UAT Test Scripts
bba.institute
Test ID | Feature / Module | Test Scenario | Test Steps | Expected Result | Actual Result | Pass/Fail | Tester | Date
UAT-001 | Login | Valid login | 1. Go to login page 2. Enter valid email 3. Enter correct password 4. Click Login | User redirected to dashboard; username shown in nav
UAT-002 | Login | Invalid password | 1. Go to login page 2. Enter valid email 3. Enter WRONG password 4. Click Login | Error message shown; user NOT logged in; attempt logged
UAT-003 | Login | Account lockout | Fail login 5 times in succession | Account locked; user notified by email; admin alerted
UAT-004 | Registration | Valid registration | 1. Go to register 2. Enter valid email, password, name 3. Submit | Account created; verification email sent within 2 min
UAT-005 | Profile | Update profile | 1. Log in 2. Go to My Profile 3. Change phone number 4. Save | New phone number saved; success message shown
UAT-006 | Product | Browse by category | 1. Log in 2. Navigate to Products 3. Select a category | Only products in selected category shown; correct count
UAT-007 | Cart | Add to cart | 1. Open product detail 2. Click Add to Cart | Item appears in cart; cart count increments
UAT-008 | Checkout | Complete purchase | 1. Add item to cart 2. Proceed to checkout 3. Enter address 4. Pay with test card | Order confirmation page shown; confirmation email received
UAT-009 | Orders | View order history | 1. Log in 2. Go to My Orders | All past orders listed; correct status; detail view opens
UAT-010 | Notifications | Order email | Place a test order | Confirmation email received within 5 min with order details