## Impact Assessment
Impact Assessment Template
bba.institute
Ref | Stakeholder / Area Affected | Nature of Impact | Type (People/Process/ Tech/Policy) | Severity (H/M/L) | Likelihood (H/M/L) | Recommended Response | Owner
IA-001 | Front-line Staff | New system replaces existing workflow — staff must learn new interface and process | People / Process | H | H | Structured training programme; change champions; go-live support for 4 weeks | Change Manager
IA-002 | Finance Team | Monthly reconciliation process changes — new report format, new system to access | People / Process | M | H | Targeted training session (2hrs); job aid / quick reference guide | BA Lead
IA-003 | IT Operations | New infrastructure to manage; increased monitoring requirements; new deployment process | Technology | M | M | Handover documentation; 2-week hypercare with dev team; runbook | Tech Lead
IA-004 | Customers (external) | New self-service portal — must re-register; UI change; new features available | People | M | H | Comms campaign 4 weeks pre-launch; guided walkthrough email; FAQ page | CX Team
IA-005 | Existing Integrations | 3 downstream systems rely on current data format — breaking change in API v2 | Technology | H | M | Negotiate migration timeline with partner teams; backward-compat layer 90 days | Integration Team
IA-006 | Regulatory Reporting | New audit log format changes compliance reporting extract | Process / Policy | H | L | Early engagement with compliance; updated report spec signed off before build | Compliance Team
IA-007 | Suppliers / Vendors | New order management system changes purchase order format | Process | L | M | Notify affected vendors 6 weeks ahead; updated EDI spec | Procurement