## Defect Log
Defect Log
bba.institute
Defect ID | Date Found | Found In (Phase) | Feature / Module | Severity (1-4) | Priority (H/M/L) | Defect Description | Steps to Reproduce | Expected Result | Actual Result | Assigned To | Status | Date Resolved
DEF-001 | 2024-02-01 | SIT | Login | 1 - Critical | H | User can log in with expired password — system not enforcing expiry | 1. Create account 2. Let password expire (test: backdate expiry) 3. Attempt login | Login rejected with 'Password expired' message | Login succeeds — dashboard shown | Dev Lead | Open
DEF-002 | 2024-02-02 | SIT | Registration | 2 - Major | H | Duplicate accounts created when form submitted twice rapidly | 1. Fill registration form 2. Click submit twice quickly | One account created; duplicate rejected | Two accounts created with same email | Backend Dev | In Progress
DEF-003 | 2024-02-03 | UAT | Cart | 2 - Major | H | Cart total does not update when item quantity changed | 1. Add item to cart 2. Change quantity from 1 to 3 | Total = unit price × 3 | Total still shows unit price × 1 | Frontend Dev | Resolved | 2024-02-05
DEF-004 | 2024-02-04 | UAT | Checkout | 3 - Minor | M | Tax amount shown as $0.00 for QLD shipping address | 1. Add item to cart 2. Enter QLD shipping address 3. Proceed to checkout | GST 10% calculated and shown | Tax field shows $0.00 | Backend Dev | Open
DEF-005 | 2024-02-05 | UAT | Notifications | 3 - Minor | M | Order confirmation email missing item images | 1. Complete test purchase | Email contains product images | Email shows broken image icons | Dev / DevOps | Open
DEF-006 | 2024-02-06 | UAT | Profile | 4 - Trivial | L | Phone field accepts non-numeric characters without validation error | 1. Go to Profile 2. Enter 'abc' in phone field 3. Save | Validation error: numbers only | Saved without error | Frontend Dev | Open
DEF-007 | 2024-02-07 | UAT | Search | 2 - Major | H | Search returns no results when search term contains apostrophe (e.g. "women's") | 1. Navigate to Products 2. Search for "women's shoes" | Results matching term shown | Zero results returned; no error | Backend Dev | In Progress